## Terala
Year wise proposals of Progressive Reclamation Plan of Terala Limestone Mine ( 49.18 ha) Mine for the year 2022-23.
Item | Details | Area in (Ha) |  | Cumilative | Quantity |  | Cumilative |  | Expenditure (Rs) |  | Cumilative
|  | Proposed | Actual |  | Proposed | Actual |  |  | Proposed | Actual
Dump Management | Area of afforested (ha) | NIL | NIL |  | NIL | NIL |  | NIL | NIL | NIL
| No.of Saplings Planted | NIL | NIL |  | NIL | NIL |  | NIL | NIL | NIL
| Cumulative No.of Plants | NIL | NIL |  | NIL | NIL |  | NIL | NIL | NIL
| Cost including watch and care during the year | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL
| Garland drain | 500 x2 x2 | 500 x2 x2
| Retaining bund | 500 x 1 x 1.5 | 500 x 1 x 1.5 |  | NIL | NIL |  | NIL | NIL | NIL
Management of Worked out Benches | Area available for rehabilitation (ha) | 100 sqm | NIL |  |  |  |  | NIL
| Afforestation done (ha) | NIL | NIL |  | NIL | NIL |  | NIL | NIL | NIL
| No.of Saplings Planted in the year | 50 | NIL |  | 50 | 50 |  | NIL | NIL | NIL
| Cumulative No.of Plants | Nil | NIL |  | NIL | NIL |  | NIL | NIL | NIL
| Any other method of rehabilitation | Nil | NIL |  | NIL | NIL |  | NIL | NIL | NIL
| Cost including watch and care during the year | Nil | NIL | Nil | NIL | Nil | NIL | NIL | Rs 10000/- | NIL
Reclamation and rehabilitation by Back filling | Void available for back filling (LXBXD) pit wise | NIL | NIL |  | NIL | NIL |  | NIL | NIL | NIL
| Void filling by watse (ha) | NIL | NIL |  | NIL | NIL |  | NIL | NIL | NIL
| Afforestation on the Back filled area (ha) | NIL | NIL |  | NIL | NIL |  | NIL | NIL | NIL
| Rehabilitation by making water reservoir pit | NIL | NIL |  | NIL | NIL |  | NIL | NIL | NIL
| Any other means | NIL | NIL |  | NIL | NIL |  | NIL | NIL | NIL
Rehabilitation on the watse land | Area available (ha) | 2.65 | 2.65 |  | NIL | NIL |  | NIL | NIL | NIL
| Area Rehabilitated (ha) | 0.55 | 0.5 |  | NIL | NIL |  | NIL | NIL | NIL
| Method of rehabilitation | Plantation | NIL |  | 300 | 300 |  | NIL | NIL | NIL
Others | i)Quarterly monitoring of Environmental Parametersin Core and Buffer Zones. | Monitoring as per guidelines |  | To be carried out | Quarterly | Quarterly |  |  | To collet the data on quarterly basis at total cost of Rs 1,00,000/- | Quarterly monitoring done by outside Agency and paid Rs 1,00,000/-
[5 empty] | Quarterly | Quarterly
[5 empty] | Quarterly | Quarterly
[5 empty] | Quarterly | Quarterly