## PMCP_Seopura Kesarpura Mine
Sheopura Kesarpura Limestone Mine, Shree Cement Ltd. Yearly Report on Protective Measures for Reclamation and Rehabilitation Work Done During The Year 2022-23
1 | Name of the mine | Sheopura Kesarpura Limestone Mine
2 | Mine code | 38RAJ01001
3 | Name of the lessee | M/s Shree Cement Limited
4 | Area in (hect.) | 856.8
5 | Village | Jhak, Lulwa
6 | Tehsil | Masuda
7 | District | Ajmer
8 | State | Rajasthan
Proposals versus achieved status on progressive mine closure plan as on 01.04.2023
Items | Details | Proposals | Remark | Actual | Remark
Dump Management | Area afforested (Ha) | Nil | Due to active dumps | 0.10 Ha | In Year 2022-23 we have additional plantation on 0.10 ha on waste dump against NIL proposal
| No of saplings planted | Nil |  | 200 nos.
| Cumulative no of plants | Nil |  | 33460
| Cost including watch and care during the year | Nil |  | Cost including mining activities
Management of worked out benches | Area avilable for rehabilitation (ha) | Nil | Due to active benches | Nil
| Afforestation done (ha) | Nil |  | Nil
| No of saplings planted in the year | Nil |  | Nil
| Cumulative no of plants | Nil |  | 900 | 0.45 ha area
| Any other method of rehabilitation (specify) | Nil |  | Nil
| Cost including watch and care during the year | Nil |  | Nil
Reclamation and Rehabilitation by Back Filling | Voids avilable for Backfilling (L x B x D) pit wise | 50 m by 100 m |  | 80 m by 100 m | 4.30 ha cum. reclaimed by plantation over back filled area. 5.05 ha cum backfliing. Expenditure common with mining activity.
| Void filled by waste | 0.50 Ha |  | 0.80 Ha
| Afforestation on backfilled area | 0.50 Ha | 1200 trees per Ha | 0.35 Ha | 250 nos of saplings
| Rehabilitation by making water reservior | Nil |  | Nil
| Any other means (specify) | Nil |  | Nil
Relabilitation of waste land within lease | Area avilable (Ha)
| Area rehabilitated (Ha) | 0.50 Ha |  | 0.50 Ha | 750 nos of saplings planted during the year on waste land within ML area.
| Method of rehabilitation | Green Belt |  | Green Belt
Others |  | Nil |  | Nil

## Sheet1 (hidden)
virgin | WD | BF
27.4 | 9.2 | 1
0.9 | 0.7 | 0.5
0.3 | 0.2 | 1
2.1 | 0.8 | 0.2
2 | 0.5 | 0.6
0.95 | 0.55 | 0.4
0 | 2.5 | 0.25
0 | 0.5 | 0.35
0.75 | 0.25 | 4.3
0.5 | 0.5
0.45 | 0.6
0.7 | 0.75
0.3 | 0.5
1.25 | 0.1
0.3 | 0.2
0.6 | 0.1
0.6 | 0.2
0.6 | 0.2
0.5 | 0
0.6 | 0.15
0.5 | 0.1
41.3 | 18.6