## Table 1
Chapter 6: PROGRESSIVE MINE CLOSURE PLAN
6.1: Status of Land
Total Area Degraded |  |  |  |  | Total mined out area Reclaimed and Rehabilitated |  |  | Other Areas Reclaimed and Rehabilitated
Total area under excavation in the lease |  | Area under Dumps (in hect) | Area under utility services (in hect) | Area unde r Stack yards (in hect) | Mined out Area Reclaimed but not rehabilitate d (in hect) | Mined out Area fully Rehabilitate d from Reclaimed area (in hect) | Area under Water Reservoir considered Rehabilitate d (in hect) | Stabililized Waste dump Rehabilitate d (in hect) | Virgin area under Green Belt (in hect)
Area under mining operatio n (Ha) | Mine d out area in the lease
5.57 | Nil | 1.46 | 0.94 | 2.14 | Nil | Nil | Nil | Nil | 5.36
During 2022-23, an additional area of 0.54Ha. will be broken up. Mining will be carried out as per the E.C capacity of 40,000 Tonnes per annum. The existing pit no.3 will be further laterally extended towards western side. Adjacent to the working pit a new dump is proposed. Environmental protective measures such as Retaining wall & Garland drain are proposed towards toe /periphery of the dump. The existing old dumps are coming within the UPL Presently there is no data regarding quality of the dump material, it is proposed to carryout detail sampling of the old dumps during 2022-23, to know if any saleable ore can be recovered from these dumps. Based on the sampling analysis, Dump working or Dump rehandling will be proposed. Hence Dump area stabilization & Development proposals are not given. The Environmental monitoring for core zone and buffer zone will be carried out as per guidelines issued by IBM vide circular No. 3/92, 2/93 and MoEF for quality of soil, Water, Air and Noise. The Environmental plan showing the monitoring location within the core zone is enclosed as Plate No. 11.
The Key Plan Showing monitoring locations of Core and Buffer zone is enclosed as Plate No. 12
Avinash R. Morey Qualified person

## Table 2
6.1: Status of Land

## Table 3
Total Area Degraded |  |  |  |  | Total mined out area Reclaimed and Rehabilitated |  |  | Other Areas Reclaimed and Rehabilitated
Total area under excavation in the lease |  | Area under Dumps (in hect) | Area under utility services (in hect) | Area unde r Stack yards (in hect) | Mined out Area Reclaimed but not rehabilitate d (in hect) | Mined out Area fully Rehabilitate d from Reclaimed area (in hect) | Area under Water Reservoir considered Rehabilitate d (in hect) | Stabililized Waste dump Rehabilitate d (in hect) | Virgin area under Green Belt (in hect)
Area under mining operatio n (Ha) | Mine d out area in the lease
5.57 | Nil | 1.46 | 0.94 | 2.14 | Nil | Nil | Nil | Nil | 5.36

## Table 4
During 2022-23, an additional area of 0.54Ha. will be broken up. Mining will be carried out as per the E.C capacity of 40,000 Tonnes per annum. The existing pit no.3 will be further laterally extended towards western side. Adjacent to the working pit a new dump is proposed. Environmental protective measures such as Retaining wall & Garland drain are proposed towards toe /periphery of the dump. The existing old dumps are coming within the UPL Presently there is no data regarding quality of the dump material, it is proposed to carryout detail sampling of the old dumps during 2022-23, to know if any saleable ore can be recovered from these dumps. Based on the sampling analysis, Dump working or Dump rehandling will be proposed. Hence Dump area stabilization & Development proposals are not given. The Environmental monitoring for core zone and buffer zone will be carried out as per guidelines issued by IBM vide circular No. 3/92, 2/93 and MoEF for quality of soil, Water, Air and Noise. The Environmental plan showing the monitoring location within the core zone is enclosed as Plate No. 11.

## Table 5
The Key Plan Showing monitoring locations of Core and Buffer zone is enclosed as Plate No. 12

## Table 6
65 ¦ P a g e Avinash R. Morey Qualified person