## PMCP_2022-23
YEARLY REPORT ON RECLAMATION AND REHABILITATION WORK DONE DURING THE YEAR 2022-23
1 | Name of the mine | Bailadila Iron Ore Mine, Deposit 5
2 | Mine code | 30MPR02005
3 | Name of the lessee | Deposit No.5
4 | Area in (hect.) | 540.05 Hec.
5 | Village | Bade Bacheli
6 | Tehsil | Bade Bacheli
7 | District | South Bastar Dantewada
8 | State | Chhattisgarh
Proposals versus achieved status on progressive mine closure plan as on 01.04.2023
1 | Afforstation
|  | Proposed during the year |  | Achieved during the year |  | Cumulative as on 01.04.2023
|  | No. of saplings | Area (ha) | No. of saplings | Area (ha) | No. of saplings | Area (ha)
| Over backfilled area | NIL | NIL | NIL | NIL | NIL | NIL
| Over dump slopes | NIL | NIL | NIL | NIL | NIL | NIL
| Other barren areas | 2750 | 1.1 | 2800 | 1.1 | 161110 | 66.93
| Outside lease area | NIL | NIL | NIL | NIL | 821557 | 328.623
2 | Backfilling (hectares) | Proposed during the year |  | Achieved during the year |  | Cumulative as on 01.04.2023
| Backfilled | NIL |  | NIL |  | NIL |  | 56800
3 | rehabilitated(ha)
| Recreation(garden/pond/lake/picnic spot) | NIL |  | NIL |  | NIL |  | 64.444
| Grassing | NIL |  | NIL |  | 5.85
| Agriculture | NIL |  | NIL |  | NIL |  | 328.6228
| Plantation & horticulture | NIL |  | NIL |  | NIL
| Water storage | NIL |  | NIL |  | NIL
| Drinking | NIL |  | NIL |  | NIL
| Irrigation | NIL |  | NIL |  | NIL
| Plants, colony , pollution control | NIL |  | NIL |  | NIL
| Pisciculture | NIL |  | NIL |  | NIL
4 | Dump stabilisation measures | Proposed during the year |  | Achieved during the year |  | Cumulative as on 01.04.2023
| Construction of parapet walls / retaining wall at toe of dumps in meters | 150 |  | 160 |  | 3190
| Construction of garland drain in meters | 125 |  | 178 |  | 1859
| Construction of settling ponds in numbers | 0 |  | 0 |  | 15
| Geo coir matting work on dump slopes in hectares | 0.35 |  | 0.35 |  | 8.72